## Tasks
Minimum List of Group Project Task |  | EEET2580 Teamwork Contribution Document
You should add more based on your group's work |  | SQUAD Samson - TEAM Job Manager
Design ERD |  | Name: Tran Minh Triet |  |  | Name: To Nhat Duy |  |  | Name: Tran Kiem Phuc |  |  | Name: Pham Quang Huy |  |  | Name: Vo Phuc Duy Nhat
Refine ERD |  | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed
MILESTONE 1
Review ERD | ERD Design | Draft and Plan ERD | 2025-10-11 | 13/11/2025 | Draft relationships between entities | 2025-10-11 | 13/11/2025 |  |  |  | Review ERD | 2025-10-11 | 13/11/2025 | Review ERD | 2025-10-11 | 13/11/2025
|  | Refine ERD with whole system | 14/11/2025 | 15/11/2025 | Define data types for attributes | 14/11/2025 | 15/11/2025 |  |  |  | Refine ERD | 14/11/2025 | 15/11/2025 | Refine ERD | 14/11/2025 | 15/11/2025
Design System Architecture for Level X Requirement RXY
Refine System Architecture for Level X Requirement RXY | Architecture Design | Draft System Context Diagram for FE | 19/11/2025 | 19/11/2025 | Draft System Context diagram for Backend | 19/11/2025 | 19/11/2025 | Draft Component diagram for Backend | 19/11/2025 | 19/11/2025 | Review Backend Component diagrams | 20/11/2025 | 20/11/2025 | Draft System Context Diagram for Frontend | 19/11/2025 | 19/11/2025
Review System Architecture for Level X Requirement RXY |  | Draft Container Diagram for FE | 19/11/2025 | 19/11/2025 | Draft Container diagram for Backend | 19/11/2025 | 19/11/2025 | Review Backend Component diagram | 19/11/2025 | 19/11/2025 | Refine Backend Component diagrams | 22/11/2025 | 24/11/2025 | Draft Container Diagram for Frontend | 19/11/2025 | 19/11/2025
|  | Draft Component Diagram for FE | 19/11/2025 | 19/11/2025 |  |  |  | Writing Backend planning document | 18/11/2025 | 19/11/2025 | Review Backend Containers diagrams | 20/11/2025 | 20/11/2025 | Review Frontend Component Diagrams | 20/11/2025 | 20/11/2025
Design UX/UI for Level X Requirement RXY |  | Refine Component Diagram for FE | 20/11/2025 | 20/11/2025 | Review Backend Component diagrams | 20/11/2025 | 20/11/2025 | Conclusion of Report | 28/11/2025 | 28/11/2025 | Refine Backend Container diagrams | 22/11/2025 | 24/11/2025 | Document Justification of Frontend Architecture | 28/11/2025 | 28/11/2025
Refine UX/UI for Level X Requirement RXY |  | Document ER Model Diagram | 28/11/2025 | 28/11/2025 | [6 empty] | Document Backend Container diagrams | 26/11/2025 | 28/11/2025 | Draft Component Diagram for Frontend | 19/11/2025 | 19/11/2025
Review UX/UI for Level X Requirement RXY |  | Document FE Component Diagram | 28/11/2025 | 28/11/2025 | Document description of Backend Container diagram | 28/11/2025 | 28/11/2025 |  |  |  | Document Backend Components diagrams | 26/11/2025 | 28/11/2025 | Refine Component Diagram for Frontend | 20/11/2025 | 20/11/2025
|  | Document justification ER Model | 28/11/2025 | 28/11/2025 | Document justification of Backend architecture | 28/11/2025 | 28/11/2025 | [6 empty] | Refine Container Diagram for Frontend | 20/11/2025 | 20/11/2025
HTML/CSS for Level X Requirement RXY |  | Refine justification FE architecture | 28/11/2025 | 28/11/2025 | [9 empty] | Document Frontend Component Diagrams | 28/11/2025 | 28/11/2025
|  | Refine Container Diagram for Frontend | 20/11/2025 | 20/11/2025 | [9 empty] | Review Frontend Container Diagram | 20/11/2025 | 20/11/2025
MILESTONE 2
SQL Queries for Level X Requirement RXY | UX / UI Design
Back-end Implementation for Level X Requirement RXY
Document [R0X] [Diagram/Justification]
Refine [R0X] [Diagram/Justification]
Review [R0X] [Diagram/Justification] | Front-end Development
Task of your own choice
Back-end Development
Reporting