## Tasks
Minimum List of Group Project Task |  | EEET2580 Teamwork Contribution Document
You should add more based on your group's work |  | SQUAD SAMSON - GROUP JOB APPLICANT
Design ERD |  | Name: Hong Thieu Kiet |  |  | Name: Tran Xuan Hoang Dat |  |  | Name: Ngo Quang Hieu |  |  | Name: Tran Quang |  |  | Name: Truong Phuoc Huy
Refine ERD |  | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed
MILESTONE 1
Review ERD | ERD Design | Design Job Profile Table ERD | 22/11/2025 | 22/11/2025 | Refine User Table ERD | 22/11/2025 | 22/11/2025 | Design User ERD | 18/11/2025 | 18/11/2025 | Review connection between User Profile and other table | 27/11/2025 | 27/11/2025 | Design Notification table ERD | 18/11/2025 | 18/11/2025
|  | Review Job Profile Table Connections ERD | 23/11/2025 | 23/11/2025 | Refine Connection between Two Squad ERD | 23/11/2025 | 23/11/2025 | Refine User ERD | 18/11/2025 | 18/11/2025
Design System Architecture for Level X Requirement RXY |  |  |  |  | Review ERD JA | 23/11/2025 | 27/11/2025
Refine System Architecture for Level X Requirement RXY | Architecture Design | Design JA System Architecture Lv3 (Component Diagram) for Frontend | 2025-11-18 | 2025-11-18 | Design JA System Architecture lv1(container diagram) Requirement for whole system | 18/11/2025 | 18/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Subcription | 27/11/2025 | 28/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Search Profile | 28/11/2025 | 28/11/2025 | Design JA System Architecture lv3(container diagram) Requirement for BE | 22/11/2025 | 22/11/2025
Review System Architecture for Level X Requirement RXY |  | Review JA System Architecture Lv2 (Modularized Component) for Frontend | 20/11/2025 | 2025-11-28 | Design JA System Architecture lv3(Component diagram) Requirement for FE Job List | 20/11/2025 | 28/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Profile | 27/11/2025 | 28/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Matching Profile | 28/11/2025 | 28/11/2025 | Design JA System Architecture lv3(components diagrams) functional Requirements for BE | 23/11/2025 | 23/11/2025
|  | Design JA System Architecture Lv3 (Component Diagram) Requirement for FE Login | 21/11/2025 | 2025-11-28 | Design JA System Architecture lv3(Component diagram) Requirement for FE Job Notification | 21/11/2025 | 28/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Application | 27/11/2025 | 28/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Job Post | 28/11/2025 | 28/11/2025 | Review JA System Architecture lv3(components diagrams) functional Requirements for BE | 25/11/2025 | 25/11/2025
Design UX/UI for Level X Requirement RXY |  | Design JA System Architecture Lv3 (Component Diagram) Requirement for FE Subscription | 21/11/2025 | 2025-11-28 | Design JA System Architecture lv3(Component diagram) Requirement for FE Job User Profile | 21/11/2025 | 28/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Notification | 2025-11-27 | 28/11/2025 | Review JA System Architecture lv3(component diagram) Requirement for BE Profile Media | 28/11/2025 | 28/11/2025 | Review JA System Architecture lv3(container diagram) Requirement for BE | 25/11/2025 | 25/11/2025
Refine UX/UI for Level X Requirement RXY |  | Design JA System Architecture Lv3 (Component Diagram) Requirement for FE Admin Panel | 21/11/2025 | 2025-11-28 | Design JA System Architecture lv3(Component diagram) Requirement for FE Job History | 21/11/2025 | 28/11/2025 | [6 empty] | Refine JA System Architecture lv3(containter diagram) Requirements for BE | 28/11/2025 | 28/11/2025
Review UX/UI for Level X Requirement RXY |  |  |  |  | Review JA System Architecture lv1(container diagram) Requirement for BE | 25/11/2025 | 28/11/2025 | [6 empty] | Refine JA System Architecture lv3(components diagrams) functional Requirements for BE | 28/11/2025 | 28/11/2025
[5 empty] | Design JA System Architecture lv2(container diagram) Requirement for FE | 18/11/2025 | 28/11/2025
HTML/CSS for Level X Requirement RXY |  |  |  |  | Refine/Adjust some JA System Architecture lv3(Component diagram) Requirement for FE | 27/11/2025 | 28/11/2025
MILESTONE 2
SQL Queries for Level X Requirement RXY | UX / UI Design
Back-end Implementation for Level X Requirement RXY
Document [R0X] [Diagram/Justification]
Refine [R0X] [Diagram/Justification]
Review [R0X] [Diagram/Justification] | Front-end Development
Task of your own choice
Back-end Development
Reporting